## AUTHORIZATION REQUEST
Facility Planning & Control
AUTHORIZATION REQUEST
PROJECT NAME: |  |  |  |  | AR NUMBER:
PROJECT & WBS NO.: |  |  |  |  | CONTRACT DATE:
CONTRACTOR: |  |  |  |  | SRM No:
SITE CODE: |  |  | STATE ID:
You are directed to make the following change(s) with costs to be deducted from Owner or Construction Manager Contingency as described herein. Attach SUMMARY, BREAKDOWN and/or UNIT PRICE BREAKDOWN forms as required and brief description of the change(s) below.
Owner Contingency (Original Contract)
Owner Contingency After Amendment #_____
Changes by Previous Authorization Request(s) (AR)
Current Adjusted Owner Contingency Balance |  |  |  |  | 0
Owner Contingency is □ unchanged □ increased by □ decreased by
New Owner Contingency Balance |  |  |  |  | 0
Construction Manager Contingency (Original Contract)
Construction Manager Contingency After Amendment #____
Changes by Previous Authorization Request(s) (AR)
Current Adjusted Construction Manager Contingency Balance |  |  |  |  | 0
Construction Manager Contingency is □ unchanged □ increased by □ decreased by
New Construction Manager Contingency Balance |  |  |  |  | 0
NOTE: 1: No additional increase in money will be considered for a Change item once the Authorization Request has been executed.
2: Time due to increase or decrease in work scope associated with this AR shall be processed via Amendment to Contract.
RECOMMENDED |  | ACCEPTED |  |  | APPROVED
Designer's Name: |  | Contractor's Name: |  |  | Project Manager:
Address: |  | Address: |  |  | Facility Planning & Control
Email Address: |  | Email Address:
By: |  | By: |  |  | By:
Date: |  | Date: |  |  | Date:
FACILITY PLANNING AND CONTROL USE ONLY
Classification | Amount |  | Classification |  | Amount
Omission (Type "O")* |  |  | Miscellaneous (Type "M")
Error (Type "E")* |  |  | Owner Requested (Type "R")
Senior Manager/Assistant Director approval:
COMMENTS:
February 2026 | [5 empty] | AR-1

## SUMMARY
CMaR Contract Authorization Request
SUMMARY
State of Louisiana |  |  |  | Item No.
Facility Planning and Control |  |  |  | RFI No. (or COR, CPR, etc.)
State Project No. |  | 0 |  | Date:
Project Name: |  | 0
Contractor Name:
Description of Work:
Subcontractor Cost Breakdowns |  |  |  | A | B |  |  | C
(See attached.)
|  |  | Breakdown | Total | OH&P |  |  | Total
| Subcontractor Name |  | No. | Direct Cost | (Max 12%) |  |  | A+(A X B)
[7 empty] | % | 0
[7 empty] | % | 0
[7 empty] | % | 0
[7 empty] | % | 0
[7 empty] | % | 0
[7 empty] | % | 0
[7 empty] | % | 0
[7 empty] | % | 0
| Subcontractor Direct Costs + Subcontractor OH&P | [6 empty] | 0
(Sum column C)
| Construction Manager's Staffing Cost | [5 empty] | % | 0
| (Sum column C times rate) |  |  |  |  | (Max: 4.66%)
| Construction Manager's Site Office Cost | [5 empty] | % | 0
| (Sum column C X rate) |  |  |  |  | (Max: 0.39%)
| General Conditions | [5 empty] | % | 0
| (Sum column C X rate) |  |  |  |  | (Max: 5%)
| Performance and Payment Bond | [5 empty] | % | 0
| (Sum column C X rate) |  |  |  |  | (Max: 0.7%)
| Builder's Risk Insurance | [5 empty] | % | 0
| (Sum column C X rate) |  |  |  |  | (Max: 5%)
| General Liability Insurance | [5 empty] | % | 0
| (Sum column C X rate) |  |  |  |  | (Max: 0.79%)
| Construction Manager's Fee | [5 empty] | % | 0
| (Sum column C X rate - only applies when accrued changes exceed 4% of the cost of the work) |  |  |  |  | (Max: 5%)
Amount will be □ unchanged □ increased by □ decreased by | [7 empty] | 0
(Sum of Change Order Subtotal and Performance and Payment Bond)
Days will be □ unchanged □ increased by □ decreased by
(Attach supporting data such as meteorological reports)
February 2026 | [7 empty] | AR-2

## BREAKDOWN
CMaR Contract Authorization Request
BREAKDOWN
State of Louisiana | [5 empty] | Breakdown No.
Facility Planning and Control | [5 empty] | Item No.
State Project No. |  |  | 0 |  |  | RFI No. (or COR, CPR, etc.)
Date:
Project Name: |  |  | 0
Subcontractor Name:
Direct Cost of Work :
| A. Labor |  | Check here if explained on the Comment Sheet | Ð |  | Hourly Wage Rate | Hours |  | Total Cost
| 1 |  |  | o |  |  |  |  | 0
| 2 |  |  | o |  |  |  |  | 0
| 3 |  |  | o |  |  |  |  | 0
| 4 |  |  | o |  |  |  |  | 0
| 5 |  |  | o |  |  |  |  | 0
| 6 |  |  | o |  |  |  |  | 0
| 7 |  |  | o |  |  |  |  | 0
[7 empty] | Sub Total |  | 0
[6 empty] | Add Labor Burden @ |  | % | 0
[7 empty] | LABOR TOTAL |  | 0
| B. Material |  |  |  | Unit Price | Unit | Units |  | Total Cost
| 1 |  |  | o |  |  |  |  | 0
| 2 |  |  | o |  |  |  |  | 0
| 3 |  |  | o |  |  |  |  | 0
| 4 |  |  | o |  |  |  |  | 0
| 5 |  |  | o |  |  |  |  | 0
| 6 |  |  | o |  |  |  |  | 0
| 7 |  |  | o |  |  |  |  | 0
|  | (Copies of invoices may be required.) |  |  |  |  | Sub Total |  | 0
[6 empty] | Add Tax @ |  | % | 0
[7 empty] | MATERIAL TOTAL |  | 0
| C. Equipment |  |  |  | Unit Rate | Unit | Units |  | Total Cost
| 1 |  |  | o |  |  |  |  | 0
| 2 |  |  | o |  |  |  |  | 0
| 3 |  |  | o |  |  |  |  | 0
| 4 |  |  | o |  |  |  |  | 0
| 5 |  |  | o |  |  |  |  | 0
| 6 |  |  | o |  |  |  |  | 0
| 7 |  |  | o |  |  |  |  | 0
|  | (Copies of invoices may be required.) |  |  |  |  | Sub Total |  | 0
[6 empty] | Add Tax @ |  | % | 0
[7 empty] | EQUIPMENT TOTAL |  | 0
| TOTAL DIRECT COST FOR THIS BREAKDOWN: | [7 empty] | 0
(Sum A, B & C)
February 2026 | [8 empty] | AR-3

## COMMENT SHEET
CMaR Contract Authorization Request
BREAKDOWN COMMENT SHEET
State of Louisiana |  |  |  | Breakdown No.
Facility Planning and Control |  |  |  | Item No.
State Project No. |  |  | 0 | RFI No. (or COR, CPR, etc.)
Date:
Project Name: |  |  | 0
Contractor/Subcontractor Name:
A. Labor
| No. | (From BREAKDOWN Sheet)
B. Material
C. Equipment
February 2026 |  |  |  |  | AR-4

## UNIT PRICE BREAKDOWN
CMaR Contract Authorization Request
UNIT PRICE BREAKDOWN
State of Louisiana |  |  |  | Breakdown No.
Facility Planning and Control |  |  |  | Item No.
State Project No. |  | 0 |  | RFI No. (or COR, CPR, etc.)
Date:
Project Name: |  | 0
Subcontractor Name:
Unit Price Tabulation
(Unit prices must be included in the bid or clearly defined in a standard, industry recognized pricing reference. The pricing reference shall be identified herein.)
| Unit Price Description |  | Reference* | Unit Price | Units | Total
0
0
0
0
0
0
0
0
0
0
0
0
* Reference Legend:
Unit Price Total: | [5 empty] | 0
(Sum Total column)
February 2026 | [5 empty] | AR-5

## Description
State of Louisiana
Division of Administration
Facility Planning and Control
Instructions for Authorization Request Back Up Forms
The General Conditions of the Contract for Construction, AIA Document A201, 2017 Edition, and the Supplementary Conditions provide for changes in the contract in the form of change orders. The costs of such changes must be carefully, clearly and accurately documented. Facility Planning & Control has prepared a set of forms to be used to provide this documentation in a consistent format that is in accordance with the Contract Documents.
Authorization Requests will typically contain one or more items of work. Each item of work will typically include work by the one or more subcontractors and/or sub-subcontractors. The documentation begins with a breakdown of the work of the subcontractor and each sub-subcontractor. This is prepared using the form entitled "BREAKDOWN." One form for each subcontractor and sub-subcontractor. Each breakdown will be summarized on the form entitled "SUMMARY." Each item of work will, in turn, be summarized on the Authorization Request itself. This should be on the face of the Authorization Request.
The forms are available as a Microsoft Excel worksheet for ease of preparation, with formulas established for mark-ups and other basic mathematical operations.
These forms are to be used as provided. Any alteration to the forms may cause the change order to be rejected.
GENERAL: |  | (Refer to Article 7 of the Supplementary and General Conditions)
Forms - There are five forms to be used for all Facility Planning and Control change orders: CHANGE ORDER form, SUMMARY, BREAKDOWN, BREAKDOWN COMMENT SHEET and UNIT PRICE BREAKDOWN. The CHANGE ORDER form is the highest level and is the official, signed document. A CHANGE ORDER form may include one or more items of work, each of which is backed up by a SUMMARY. Each SUMMARY will be backed up with one or more BREAKDOWNs. Any unusual rates, unit costs or quantities may be explained on the COMMENT SHEET. It's simple. The BREAKDOWN form must be used for the general contractor and any subcontractor or sub-subcontractor, at any level, that is to get OH&P. Use as many as needed.
Unit Pricing - Labor, material and equipment breakdown is the standard method of pricing Authorization Requests for Facility Planning and Control. However, unit pricing may be considered in some circumstances if the unit prices are clearly established such as by unit prices that were included in the bid. These prices may also be derived from a construction industry standard reference such as R.S. Means. If unit prices were included in the bid proposal they are acceptable for pricing Authorization Request work and, in fact, must be used for any work that is included in the Authorization for which they were established . The UNIT PRICE BREAKDOWN is provided for this purpose.
AUTHORIZATION REQUEST:
Project identification information: Complete as required. The Site Code, State ID and CFMS / SRM No(s). (contract numbers) can be obtained from the FP&C Project Manager.
Description: This will include a list of each attached SUMMARY that makes up this Authorization Request and a brief statement of the work included in each.
New Contract Sum: Calculate the new contract amount using the original contract amount, previous Authorization Requests and the new Authorization Request. Select the appropriate word for increase, decrease or unchanged, and delete the terms that don't apply.
RECOMMENDED: Show the Designer's name and address, sign on the line indicated as "By:" and date on the indicated line.
ACCEPTED: Show the Contractor's name and address, sign on the line indicated as "By:" and date on the indicated line.
APPROVED: For approval by FP&C.
SUMMARY: |  | (Refer to Article 7 of the Supplementary and General Conditions)
Item No.: Show the Item number as it will appear on the Authorization Request Form. Note: This may be one of several items included in one Authorization Request form.
RFI No.: Show the number of the request for information. This may be known by another name such as ARP (Authorization Request Proposal) CPR (Change Proposal Request,) etc.
Project No., WBS No., Date, Project Name. Complete as appropriate.
Contractor: Name of General Contractor.
Description of Work: Give a brief description of the work included in this Item.
General Contractor Direct Costs: Show the total General Contractor Cost from the BREAKDOWN and show the Breakdown No. in the space provided.
General Contractor Total Cost: Show the total General Contractor Cost plus the General Contractor's overhead and profit. The overhead and profit shall not exceed 8% of the Direct Cost.
Subcontractor Cost Breakdowns: List each subcontractor, Breakdown No. and Total Direct Cost (in column "A") from the attached BREAKDOWN sheets. Show the subcontractor's overhead and profit percentage in column "B" and show the calculated total of the direct cost plus the percentage of the direct cost in column "C." If the electronic version of the form is being used, column "C" will be automatically calculated. The overhead and profit shall not exceed 8% of the Total Direct Cost.
Subcontractor Direct Costs Total: Sum of column "A." This will be used to calculate the General Contractor's overhead and profit on the subcontractors' work. If the electronic version is being used, this will be an automatic calculation.
Subcontractor Direct Costs + Subcontractor OH&P: Sum of column "C." This represents the total amount that subcontractors will be paid. Automatic calculation.
Indirect Costs - Enter percentage and calculate the amount for the indirect cost.
Construction Manager Fee (only applies when accrued changes exceed 4% of the cost of the work) - Enter percentage and calculate the amount for the fee.
Amount will be (increased) (decreased) (unchanged) by: Add/calculate total Authorization Request amount. Indicate "increase," "decrease" or "unchanged", and delete the terms that don't apply.
Days will be (increased) (decreased) (unchanged) by: Show the number of days to be added or deleted from the contract, if any, due to changes in scope, adverse weather, unusual delays or other factors, only if it is proven the critical path is affected. Note that a change in scope does not necessarily indicate a change in time. Indicate "increased," "decreased" or "unchanged", and delete the terms that don't apply.
BREAKDOWN:
Item No. Show the Item number as it will appear on the Authorization Request Form and the SUMMARY. Note: This may be one of several items included in one CHANGE ORDER form.
RFI No.: Show the number of the request for information. This may be known by another name such as ARP (Authorization Request Proposal), CPR (Change Proposal Request), etc.
Project No., WBS No., Date, Project Name. Complete as appropriate.
Subcontractor: Name of Subcontractor or Sub-subcontractor.
Direct Cost of Work:
Check here if explained on the Comment Sheet: If rates, unit costs or quantities may appear unreasonable compared to standard costs or quantities the reasons may be explained on the attached comment sheet and the box checked to indicate that there is an explanation.
A. Labor: Include the “wages paid” hourly direct labor and/or foreman necessary to perform the required change. “Wages paid” is the amount actually paid the employee, not the fully burdened charge rate used in the bid, etc. Supervisory personnel in district or home office shall not be included. Do not include the project superintendent, except as permitted by Section 7.2 of Supplementary Conditions. Supervisory personnel on the job-site, but with broad supervisory responsibility shall not be included as Direct Labor, except as permitted by Section 7.2 of Supplementary Conditions. Typically there will be only one superintendent on the job and his/her time shall not be included, except as permitted by Section 7.2 of Supplementary Conditions. Typically all other employees are eligible for inclusion. List by job title each person employed on the work, his/her hourly rate, the number hours work and the extended Total Cost. Do not list crews unless the rates for them are readily available in standard cost estimating references such as R. S. Means. Add the labor burden that was provided at the Pre-Construction conference and in compliance with the Contract Documents, and total the amounts in LABOR TOTAL.
B. Material: Include the acquisition cost of all materials directly required to perform the required change. List each material used in the work, the price per unit, name of the unit, the number of units used and the extended Total Cost. Add the tax rate and tax and total the amounts in MATERIAL TOTAL.
C. Equipment: Include the rental cost of equipment items necessary to perform the change. For company-owned equipment items, include documentation of internal rental rates submitted at the pre-construction conference. Charges for small tools, and craft specific tools are not allowed. List each piece of equipment used in the work, the rate by units of time (hour, day, week, etc.,) number of units of time the piece was in service on the work and the extended total cost. Add the tax rate, calculate the tax and total the amounts in EQUIPMENT TOTAL.
TOTAL DIRECT COST FOR THIS BREAKDOWN: Total of A. Labor, B. Material and C. Equipment. This is the amount that will be carried forward to the SUMMARY Sheet. This amount does NOT include Overhead and Profit. This will be added on the SUMMARY Sheet.
COMMENTS SHEET:
The COMMENTS SHEET uses the same heading as the SUMMARY and BREAKDOWN.
The COMMENTS SHEET includes three sections, one each for A. Labor, B. Materials and C. Equipment. These correspond to the sections in the BREAKDOWN. Each comment should be entered in the section to which it corresponds on the BREAKDOWN and numbered to correspond to the appropriate line. Comments are to used only to explain unusual rates, costs or quantities.
UNIT PRICE BREAKDOWN:
The UNIT PRICE BREAKDOWN uses the same heading as the BREAKDOWN.
The UNIT PRICE BREAKDOWN is similar to the BREAKDOWN.
Unit Price Tabulation: Each unit price is listed along with its corresponding price and the number of units used in the work. The price and number of units are multiplied to provide the total cost of each unit price item. The pricing reference, such as the bid form for the project or a construction industry standard reference, must be cited for each unit price. This may be more fully described in "Reference Legend,"
Unit Price Total: Sum the unit prices to obtain the total cost for unit prices.
February 2026 |  |  | AR-6

## DIAGRAM
| AUTHORIZATION REQUEST Diagram of a typical AR structure. |  |  | Construction Contract Change Order AUTHORIZATION REQUEST __________________________ __________________________ __________________________ __________________________ __________________________ __________________________ __________________________________________________________ ------------- ------------- ___________________________________________________________
|  | Construction Contract Change Order SUMMARY ___________________________ ___________________________ ________________________ ________________________ ________________________ ________________________ ___________________________ ___________________________ |  |  |  | Construction Contract Change Order SUMMARY ___________________________ ___________________________ ________________________ ________________________ ________________________ ________________________ ___________________________ ___________________________
| Construction Contract Change Order BREAKDOWN ___________________________ ___________________________ ________________________ ________________________ ________________________ ________________________ ___________________________ ___________________________ ___________________________ _______________________ | Construction Contract Change Order BREAKDOWN ___________________________ ___________________________ ________________________ ________________________ ________________________ ________________________ ___________________________ ___________________________ ___________________________ _______________________ | Construction Contract Change Order BREAKDOWN ___________________________ ___________________________ ________________________ ________________________ ________________________ ________________________ ___________________________ ___________________________ ___________________________ _______________________ |  | Construction Contract Change Order BREAKDOWN ___________________________ ___________________________ ________________________ ________________________ ________________________ ________________________ ___________________________ ___________________________ ___________________________ _______________________ | Construction Contract Change Order BREAKDOWN ___________________________ ___________________________ ________________________ ________________________ ________________________ ________________________ ___________________________ ___________________________ ___________________________ _______________________ | Construction Contract Change Order BREAKDOWN ___________________________ ___________________________ ________________________ ________________________ ________________________ ________________________ ___________________________ ___________________________ ___________________________ _______________________ | Construction Contract Change Order BREAKDOWN ___________________________ ___________________________ ________________________ ________________________ ________________________ ________________________ ___________________________ ___________________________ ___________________________ _______________________
|  | Construction Contract Change Order BREAKDOWN COMMENT SHEET __________________________ __________________________ __________________________ __________________________ __________________________ __________________________ |  |  |  |  | Construction Contract Change Order BREAKDOWN COMMENT SHEET __________________________ __________________________ __________________________ __________________________ __________________________ __________________________
February 2026 | [7 empty] | AR-7